## Sheet1
ESC EXAMPLE WORKSHOP TIMELINE
Countdown |  | Committees
Wks Prior
26 weeks |  |  | Establish Workshop Leadership and form Committees
Obtain concurrence on program - main issues
24 weeks |  | A | DETERMINE LOCATION / DATE / FACILITY USE COSTS & FOOD SVC. COSTS
Cross check conflicting program/event dates, holidays, etc.
|  | B | Contact / Confirm Speakers
|  | C | Initiate Program Brochure Copy Development
|  | D | Mail and E-Mail List - Develop/Generate
18 weeks |  | C | PROGRAM BROCHURE COPY COMPLETE except speakers/topics
|  | C | Develop E-Mail Workshop Alerts
|  | C,F | Develop Vendor/Program Supporter E-Mail
16 weeks |  | C,D | E-mail Workshop Alerts - DATE/TIMES/FEES FIXED Complete speaker confirmation not needed
10 weeks |  | B,C | ALL SPEAKERS/TOPICS CONFIRMED, FINALIZE PROGRAM BROCHURE COPY
9 weeks |  | E | PRINT BROCHURES
8 weeks |  | E | MAIL OUT / BROADCAST E-MAIL BROCHURES
|  | B | HANDOUT MAT'L BINDERS Cover Art/Spines/Tabs Complete
4 weeks |  | F | CUT-OFF DATE FOR TTD without additional late fee
|  | G | MAKE INITIAL ARRANGEMENTS FOR BREAKS / LUNCHES
|  | H | DUPLICATE HANDOUT MATERIALS
3 weeks |  | H | PURCHASE BINDERS / ASSEMBLE NOTEBOOKS
2 weeks |  | G | FINALIZE ARRANGEMENTS FOR BREAKS / LUNCHES
Workshop |  | I | DAY of EVENT COORDINATION
Week
| COMMITTEES | A | Facility Coordination - Secure dates, verify space reqmt's (registration,mtg room,TTD area,reception,rooms, media needs and obtain key contact names/numbers)
|  | B | Speaker Coordination - Obtain speaker commitment, coordinate re:handouts, media needs, bio-sketch
|  | C | Publications Coordination - Develop program brochure copy, e-mail alerts, Vendor/Program Supporter Info Package
|  | D | E-Mail / Mailing Lists (Potential attendees and vendor/supporters) - Send out Workshop Alerts and Vendor/Supporter E-mail
|  | E | Printing / Mailing Coordination
|  | F | Vendor/Supporter Coordination - Interface and coordinate TTD, materials for handout binders
|  | G | Food Services Coordination - Lunches, Breaks, Reception
|  | H | Handout Binder Coordination - Duplicate, assemble binders, purchase binders
|  | I | Day of Event Coordination - Registration (name tags), media set-ups, room arrangements